## Blank
Resource Breakdown Structure Project Name: New Hire Orientation Program Date: 16 December 2024
WBS Identifier # | Work Package | Internal Personal Required | External Personnel Required | Venue Costs | Materials Required | Supplies Required | Equipment Required | Comments | Total Direct Costs
1.1.1 | Manage Venue |  |  | 5000 |  |  |  | corporate conf room | 5000
1.1.2 | Develop Catering Plan |  |  |  | 400 |  |  | food costs | 400
1.1.3 | Manage Speakers
1.1.4 | Develop AV Plan | [5 empty] | 200 | IT costs | 200
1.1.5 | Develop Employee Supply List |  |  |  | 400 |  |  | marketing | 400
1.1.6 | Develop/Approve Agenda & Plan | 14730 | [5 empty] | employee time (60%) | 14730
2.1.1 | Prepare Venue
2.1.2 | Implement Catering Plan
2.1.3 | Welcome Speakers
2.1.4 | Verify AV
2.1.5 | Issue/Account for Employee Supplies |  |  |  |  | 9600 |  | new issue | 9600
2.1.6 | Implement Event
3.1.1 | Close Orientation | 4910 | [5 empty] | employee time (20%) | 4910
3.1.2 | Close Venue | 4910 | [5 empty] | employee time (20%) | 4910
3.1.3 | Solicit Feedback
3.1.4 | Conduct Lessons Learned
TOTAL COSTS |  | 24550 | 0 | 5000 | 800 | 9600 | 200 | 0 | 40150
Contingency Requirements (10%) | [8 empty] | 4015
Personnel Cost Requirements | [5 empty] | Note: Update Cost Categories to reflect actual project requirements
Rate | Name | Hours | Costs
50 | Marcus Wilson | 28 | 1400
50 | Gloria Fisher | 280 | 14000
50 | Hiroshi Tanaka/IT | 20 | 1000
50 | Ursula Miller | 2 | 100
50 | Priya Sanders | 25 | 1250
50 | Sam Manning | 10 | 500
50 | Sunny Marsh | 3 | 150
50 | Ram Finland | 3 | 150
50 | 12 new employees | 120 | 6000
TOTAL |  |  | 24550

## Demo Example
Resource Breakdown Structure: "Hierarchical breakout of resources by category and type" Project Name: Annual Executive Meeting Support Project Date: 30 April 20XX
WBS Identifier # | Work Package | Personnel Costs | Beverage Costs | Catering Costs | Support Costs | Venue Support | Comments | Total Direct Costs
1.1.1 | Define Venue |  |  |  |  | 1000 | Initial Deposit | 1000
1.1.2 | Determine Attendees |  |  |  | 1500 |  | Handouts/Print | 1500
1.1.3 | Plan Team | [6 empty] | 0
1.1.4 | Plan Beverages |  | 500 |  |  |  | Coffee/Juice | 500
1.1.5 | Plan Catering |  |  | 1000 |  |  | Box Lunches | 1000
2.1.1 | Assemble Packages | [6 empty] | 0
2.1.2 | Install AV | [6 empty] | 0
2.1.3 | Set Up Venue | [6 empty] | 0
2.1.4 | Conduct Meet |  |  |  | 1000 |  | AV/IT Support | 1000
3.1.1 | Close Out Venue | 600 |  |  |  | 1000 | Clean/Venue $ | 1600
3.1.2 | Prepare Final Reports | [6 empty] | 0
3.1.3 | Pay Outstanding Invoices | 30 |  |  |  |  | Bookkeeper | 30
3.1.4 | Perform Lessons Learned | [6 empty] | 0
TOTAL COSTS |  | 630 | 500 | 1000 | 2500 | 2000 | 0 | 6630
Contingency Requirements (10%) | [7 empty] | 663