## Communication Plan Template
Communications Plan for Project:
Communications Item Forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format Medium (How) (Where) | Purpose (Why)
Weekly Project Status Meeting | Juan Cortez | Project Team | Weekly, Wednesdays at 2:00 p.m. | Main Conference Room | Review status, discuss open issues/risks, review project deliverables.
Sponsor 1:1 Meeting | Roger Jones | Sandra Morgan | Twice a week, Mon/Wed 9:00-9:30 a.m. | Sarah's Office | Update the project sponsor on status, discuss needs, review change requests.
Weekly Project Status Report | Roger Jones | All Key Stakeholders | Weekly, due by Friday at 10:00 a.m. | SharePoint | Provide an overview of key project status issues.
Change Control Board (CCB) Meeting | Sarah Kim | All Key Stakeholders | Every two weeks, Mondays at 10:00 a.m. | Main Conference Room | Review and approve/disapprove change requests.
Vendor Source Selection | Sarah Kim | Kyoko Tanaka, Catering Rep | March 11 at 10:00 a.m. | Sarah's Office | Finalize catering and trainer contracts.
Training Roster Confirmation | Sarah Kim | Kyoko Tanaka | March 21 at 11:00 a.m. | Sarah's Office | Finalize training roster to maximize attendance.
Conference Room Preparation | Roger Jones | Project Team | March 30 from 1:00-3:00 p.m. | Main Conference Room | Set up the main conference room for the training event.
Version: 01 |  |  | Date: