## Blank
Resource Breakdown Structure Project Name: Date:
WBS Identifier # | Work Package | Internal Personal Required | External Personnel Required | Venue Costs | Materials Required | Supplies Required | Equipment Required | Comments | Start Date | Finish Date | Total Direct Costs
1.1.1 | Define Venue |  |  | 5000 |  |  |  | corporate conf room |  |  | 5000
1.1.2 | Develop Venue Logistics Plan |  |  |  | 400 |  |  | food costs |  |  | 400
1.1.3 | Plan Attendees and Speakers
1.1.4 | Define Marketing Collateral | [5 empty] | 200 |  |  |  | 200
1.1.5 | Develop Catering Plan |  |  |  | 400 |  |  | IT costs |  |  | 400
1.1.6 | Finalize Funding Plan | 1580 | [5 empty] | marketing |  |  | 1580
1.1.7 | Plan Approval | [6 empty] | employee time (60%)
2.1.1 | Begin Event Preparations
2.1.2 | Distribute Event Materials (Virtual)
2.1.3 | Prepare Venue / Attendees / Speakers
2.1.4 | Distribute Event Materials (On-Site) | [5 empty] | 9600 | new issue |  |  | 9600
2.1.5 | Conduct Event / Catering Plan
2.1.6 | Close Event | [6 empty] | employee time (20%)
3.1.1 | Pay Invoices | 4500 | [5 empty] | employee time (20%) |  |  | 4500
3.1.2 | Conduct Lessons Learned | 4500 | [8 empty] | 4500
3.1.3 | Plan Next Steps
TOTAL COSTS |  | 10580 | 0 | 5000 | 800 | 0 | 9800 |  |  |  | 26180
Total Contingency Requirements (10%) | [10 empty] | 2618
Personnel Cost Requirements | [5 empty] | Note: Update Cost Categories to reflect actual project requirements
Rate | Name | Hours | Costs
50 | Juan Cortez | 18 | 900
50 | Ramesh Patel | 200 | 10000
50 | Michael Watson | 20 | 1000
50 | Sophia Lamar | 35 | 1750
50 | Priya Singh | 40 | 2000
50 | Ann | 30 | 1500
50 | Valerie Shannon | 28 | 1400
TOTAL |  |  | 18550

## Demo Example
Resource Breakdown Structure: "Hierarchical breakout of resources by category and type" Project Name: Annual Executive Meeting Support Project Date: 30 April 20XX
WBS Identifier # | Work Package | Personnel Costs | Beverage Costs | Catering Costs | Support Costs | Venue Support | Comments | Total Direct Costs
1.1.1 | Define Venue |  |  |  |  | 1000 | Initial Deposit | 1000
1.1.2 | Determine Attendees |  |  |  | 1500 |  | Handouts/Print | 1500
1.1.3 | Plan Team | [6 empty] | 0
1.1.4 | Plan Beverages |  | 500 |  |  |  | Coffee/Juice | 500
1.1.5 | Plan Catering |  |  | 1000 |  |  | Box Lunches | 1000
2.1.1 | Assemble Packages | [6 empty] | 0
2.1.2 | Install AV | [6 empty] | 0
2.1.3 | Set Up Venue | [6 empty] | 0
2.1.4 | Conduct Meet |  |  |  | 1000 |  | AV/IT Support | 1000
3.1.1 | Close Out Venue | 600 |  |  |  | 1000 | Clean/Venue $ | 1600
3.1.2 | Prepare Final Reports | [6 empty] | 0
3.1.3 | Pay Outstanding Invoices | 30 |  |  |  |  | Bookkeeper | 30
3.1.4 | Perform Lessons Learned | [6 empty] | 0
TOTAL COSTS |  | 630 | 500 | 1000 | 2500 | 2000 | 0 | 6630
Contingency Requirements (10%) | [7 empty] | 663